## Terms of Use
DISCLAIMER AND TERMS OF USE This POA&M template is provided "AS IS" for informational and educational purposes only. By downloading, accessing, or using this spreadsheet, you acknowledge and agree to the following: User Responsibility: You assume full responsibility for the use of this template and any decisions made based on its contents. This template is intended as a starting point only and does not constitute professional cybersecurity, legal, or compliance advice. No Liability: The creator(s) shall not be liable for any damages, losses, or consequences arising from the use or inability to use this template, including but not limited to direct, indirect, incidental, or consequential damages. Compliance Responsibility: You are solely responsible for ensuring compliance with applicable laws, regulations, industry standards, and organizational policies. You must validate, customize, and maintain this template according to your specific requirements. Professional Consultation: For specific cybersecurity, legal, or compliance guidance, consult qualified professionals. By using this template, you acknowledge that you have read, understood, and agree to be bound by these terms.

## Dashboard
POA&M Dashboard
Generated: July 15, 2025
Total Items | Open Items | High/Very High Risk | Overdue Items | Quick Wins | Completion Rate
18 | 9 | 14 | 17 | 9 | 5.556%
Risk Level | Count
Very High | 4
High | 10
Moderate | 4
Low | 0
Status | Count
Open | 9
Ongoing | 7
Completed | 1
Delayed | 1

## POA&M Items
POA&M ID | Control Family | Control ID | Weakness Description | Risk Level | Status | Planned Actions | Resources Needed | Estimated Cost | Effort Level | Owner | Target Date | Milestone | Progress % | Quick Win | Implementation Notes
POA-001 | AC | AC-2 | No formal account management procedures. User accounts not regularly reviewed. | High | Ongoing | Implement automated user access review using PowerShell scripts | IT Admin (20hrs) | Free | Low | IT Admin | 2025-08-14 12:15 | Quarterly review process | 60 | Yes | Using PowerShell script template from NIST guide. Testing in dev environment.
POA-002 | IA | IA-2(1) | Multi-factor authentication not implemented for privileged accounts | Very High | Open | Deploy Microsoft MFA for all admin accounts | Azure AD P1 licenses, IT training | Low ($0-$1K) | Medium | IT Security Lead | 2025-07-30 12:15 | 100% admin MFA coverage | 15 | No | License procurement approved. Pilot with 3 admin accounts scheduled.
POA-003 | CM | CM-2 | No baseline configurations documented for servers and workstations | High | Completed | Document baseline configs using CIS Benchmarks | Systems admin (30hrs) | Free | Low | Systems Admin | 2025-07-10 12:15 | All systems documented | 100 | Yes | Completed using CIS Benchmark templates. Documentation in SharePoint.
POA-004 | AU | AU-6 | Log analysis performed manually and infrequently. No automated alerting | Moderate | Ongoing | Configure Windows Event Forwarding and PowerShell log analysis | IT Admin (15hrs) | Free | Low | IT Admin | 2025-08-29 12:15 | Automated daily log review | 40 | Yes | WEF configured for domain controllers. Working on member servers.
POA-005 | IR | IR-4 | Incident response plan exists but never tested or exercised | High | Delayed | Conduct tabletop exercise and update IR plan | External facilitator, staff time | Medium ($1K-$10K) | Medium | Security Manager | 2025-06-30 12:15 | Successful tabletop exercise | 25 | No | Delayed due to budget approval. Exploring free CISA resources as alternative.
POA-006 | RA | RA-5 | Vulnerability scanning not performed regularly | Moderate | Open | Implement Nessus Essentials for vulnerability scanning | IT Security (20hrs) | Free | Low | IT Security | 2025-09-13 12:15 | Monthly vuln scans | 0 | Yes | Researching Nessus Essentials vs OpenVAS. Need network discovery first.
POA-007 | SC | SC-7 | Network segmentation insufficient. Flat network allows lateral movement | High | Ongoing | Implement VLAN segmentation for servers and workstations | Network engineer (40hrs) | High ($10K+) | High | Network Admin | 2025-10-13 12:15 | Complete network segmentation | 30 | No | Network assessment complete. Switch procurement in progress.
POA-008 | CP | CP-1 | Business continuity plan doesn't address cybersecurity incidents | Moderate | Open | Update BCP to include cyber incident scenarios | BCP team, legal review | Low ($0-$1K) | Medium | Risk Manager | 2025-09-28 12:15 | Updated BCP with cyber scenarios | 10 | Yes | Working with legal team on compliance requirements. Draft scenarios ready.
POA-009 | AT | AT-2 | Security awareness training not provided to all staff | High | Ongoing | Deploy online security awareness training platform | Training licenses, HR coordination | Medium ($1K-$10K) | Medium | HR Manager | 2025-08-29 12:15 | 90% staff completion | 70 | No | KnowBe4 pilot successful. Rolling out to all departments. Q3 completion target.
POA-010 | PE | PE-3 | Physical access controls insufficient for server room | High | Open | Install card reader system and security cameras | Card readers, cameras, installation | Medium ($1K-$10K) | Medium | Facilities | 2025-08-14 12:15 | Restricted physical access | 0 | No | Quotes obtained from 3 vendors. Selecting system with integration capabilities.
POA-011 | MP | MP-6 | Removable media not encrypted or tracked | High | Open | Implement BitLocker To Go for all USB devices | BitLocker licenses and policy enforcement | Low ($0-$1K) | Low | IT Security | 2025-08-20 | All removable media encrypted | 25 | Yes | Testing BitLocker To Go deployment. Policy draft complete.
POA-012 | PS | PS-3 | No background checks for contractors with system access | Very High | Ongoing | Establish contractor screening process with HR | HR resources and screening vendor | Medium ($1K-$10K) | Medium | HR Manager | 2025-07-25 | All contractors screened | 60 | No | Working with third-party screening company. 5 contractors pending.
POA-013 | SI | SI-4 | No file integrity monitoring on critical systems | High | Open | Deploy AIDE or Tripwire for system integrity checking | Open source tools and admin time | Free | Medium | Systems Admin | 2025-09-10 | Critical systems monitored | 15 | Yes | Researching AIDE vs Tripwire. Testing on dev servers first.
POA-014 | MA | MA-2 | Maintenance activities not logged or tracked | Moderate | Open | Create maintenance log system using SharePoint | SharePoint configuration and training | Free | Low | IT Admin | 2025-08-05 | All maintenance logged | 40 | Yes | SharePoint list created. Training IT staff on logging procedures.
POA-015 | PL | PL-2 | Security plan outdated and not reviewed annually | High | Ongoing | Update and establish annual security plan review | Security team time and management review | Low ($0-$1K) | Medium | CISO | 2025-06-15 | Current security plan approved | 20 | No | Delayed due to resource constraints. Draft 60% complete.
POA-016 | SR | SR-2 | Third-party vendors not assessed for security risks | Very High | Open | Implement vendor risk assessment questionnaire | Vendor management process and reviews | Medium ($1K-$10K) | High | Procurement | 2025-09-30 | All vendors risk-assessed | 5 | No | Developing assessment criteria. Legal reviewing contract language.
POA-017 | AC | AC-17 | Remote access not properly secured with VPN | Very High | Ongoing | Deploy always-on VPN for all remote workers | VPN licenses and endpoint configuration | Medium ($1K-$10K) | Medium | Network Admin | 2025-05-28 | 100% remote VPN coverage | 75 | No | 80% of users migrated to new VPN. Scheduling remaining users.
POA-018 | AU | AU-12 | Audit logs not generated for application activities | High | Open | Enable application-level logging for business apps | Development team and log storage | Low ($0-$1K) | Medium | Dev Team Lead | 2025-08-15 | All apps generating audit logs | 30 | Yes | Implemented for 3 of 8 applications. Working on database logging.

## Reference Data
Control Family | Family Code | Description | Common Weaknesses | Risk Levels | Status Options | Effort Levels | Budget Categories
Access Control | AC | Managing user access to systems and data | No MFA, Excessive privileges, Shared accounts | Very High | Open | Low | Free
Awareness and Training | AT | Security awareness and training programs | No security training, Outdated awareness | High | Ongoing | Medium | Low ($0-$1K)
Audit and Accountability | AU | Logging, monitoring, and audit trails | No log review, Missing audit trails | Moderate | Completed | High | Medium ($1K-$10K)
Configuration Management | CM | Baseline configurations and change control | No baselines, Uncontrolled changes | Low | Delayed |  | High ($10K+)
Contingency Planning | CP | Business continuity and disaster recovery | No BCP, Untested recovery procedures |  | Cancelled
Identification and Authentication | IA | User identity verification | Weak passwords, No MFA
Incident Response | IR | Security incident handling procedures | No IR plan, Untested procedures
Maintenance | MA | System maintenance and updates | Missing patches, No maintenance schedule
Media Protection | MP | Protecting removable media and storage | Unencrypted media, No disposal process
Personnel Security | PS | Background checks and personnel policies | No background checks, Insider threats
Physical Protection | PE | Physical security controls | Unsecured facilities, No access logs
Planning | PL | Security planning and governance | No security plan, Unclear policies
Risk Assessment | RA | Risk identification and management | No risk assessment, Outdated risk analysis
System and Communications Protection | SC | Network and system security | No encryption, Poor network segmentation
System and Information Integrity | SI | System integrity monitoring | No integrity monitoring, Missing AV
Supply Chain Risk Management | SR | Third-party risk management | Unvetted vendors, No supplier assessment

## Templates
POA&M Templates & Quick Reference
Common Team POA&M Items
Control ID | Weakness | Quick Fix | Effort | Cost
AC-2 | No account review process | PowerShell script for AD user audit | Low | Free
IA-2(1) | No MFA for admins | Enable Azure MFA | Medium | Low
CM-2 | No configuration baselines | Use CIS Benchmarks | Low | Free
AU-6 | Manual log review | Windows Event Forwarding | Low | Free
RA-5 | No vulnerability scanning | Nessus Essentials | Low | Free
CP-1 | BCP missing cyber scenarios | Update existing BCP | Medium | Low
AT-2 | No security awareness | KnowBe4 or similar platform | Medium | Medium
PE-3 | Poor physical security | Badge readers + cameras | Medium | Medium